## PERT
Activity_ID | Activity_name | Dependence
A | Requirement(fundamental analysis) | B | 3 | 4 | 5 | 4 | 4 | 0.11111 | 0.33333
B | Requirement(specification) | A,C | 3 | 2 | 5 | 2.6667 | 2 | 0.11111 | 0.33333
C | Design | B,D | 4 | 3 | 7 | 3.8333 | 6 | 0.25 | 0.5
D | Development(Meeting) | C,E,F | 4 | 6 | 7 | 5.8333 | 6 | 0.25 | 0.5
E | Development(sprint1) | D,G,H,I | 14 | 18 | 21 | 17.8333 | 16 | 1.3611 | 1.1667
F | Development(sprint2) | D,I,J | 15 | 19 | 21 | 18.6667 | 10 | 1 | 1
G | Testing(black-box testing) | E | 3 | 5 | 7 | 5 | 5 | 0.44444 | 0.66667
H | Testing(white-box testing) | E | 4 | 5 | 7 | 5.1667 | 5 | 0.25 | 0.5
I | Testing(unit testing) | E,F | 4 | 8 | 10 | 7.6667 | 5 | 1 | 1
J | Testing(automatic testing) | F | 5 | 7 | 10 | 7.1667 | 12 | 0.69444 | 0.83333
|  |  | 59 | 77 | 100 | 77.8333 | 71 | 2.3393 | 1.5295
Optimistic time (O) |  |  | MIN | MAX
Pessimistic time (P) |  | 68.26% | 77 | 80
Most Likely time (M) |  | 95.46% | 75 | 81
Expected time (E) |  | 99.73% | 74 | 83
Duration time (D) |  | 99.99% | 69 | 88
𝜎^2
𝑡_𝑚
𝑡_𝑜
𝑡_𝑝
𝑡_𝑒
σ
𝑡_𝑑
𝑡_𝑒±𝜎
𝑡_𝑒±2𝜎
𝑡_𝑒±3𝜎
𝑡_𝑒±6𝜎

## GANTT
Activity_ID | Activity_name | start_date(original) | duration_time
A | Requirement(fundamental analysis) | 2021-09-06 | 4
B | Requirement(specification) | 2021-09-08 | 2
C | Design | 2021-09-15 | 6
D | Development(meeting) | 2021-09-26 | 6
E | Development(sprint1) | 2021-09-26 | 16
F | Development(sprint2) | 2021-11-01 | 10
G | Testing(black-box testing) | 2021-10-12 | 5
H | Testing(white-box testing) | 2021-10-17 | 5
I | Testing(unit testing) | 2021-10-20 | 5
J | Testing(automatic testing) | 2021-11-18 | 12
71
Sep, 6
Sep, 8
Sep, 15
Sep, 26
Sep, 26
Nov, 1
Oct, 12
Oct, 17
Oct, 20
Nov, 18